## Sheet1
Product Backlog
ID | As a… | I want to be able to… | So that… | Priority | Sprint | Status
1 | User | have message on a screen | it is properly displayed | Must | 1 | Completed
2 | User | have feedback | there is messages sent and recieved | Must | 1 | Completed
3 | User | typing through text or manual Morse Code | I may send message | Must | 1 | Completed
4 | User | have a recieving signal from device | insure connectivity | Must | 1 | Completed
5 | User | a message was succefully sent | I can verify connection | Must | 2 | To be Started
6 | Sender | be able to recieve message being sent | I can view the message | Must | 2 | To be Started
7 | Receiver | view message on LCD screen display | I can read the message | Must | 2 | To be Started
8 | User | input message through keyboard | so that I am bale to type my message | Should | 2 | To be Started
9 | User | have a button to send could through Morse code Munally | I am able send manual message | Could | 2 | To be Started
10 | User | edit text before sending | I have freedom to my wording | Could
11 | User | view errors in transmition | I know an error occured | Should
12 | User | veiw and delete part of a text | I can have freedom to edit | Could
13 | User | have a comfirmation message before sending text | I can verify text | Could
14 | User | distiguish connected devices based on LED light | I can tell who is sending a message through color | Could
15 | User | pick the color of the LED for sending device | I can have freedom to commmunicate with different groups | Could
16 | User | view the color of LED on the receiving device | I can see who is communicating through color | Could
Sprint Backlog
Task ID | Responsible | Start | End | Days | Status
Sprint 1 |  | 2018-08-27 | 2018-09-16 |  | Complete
1 | Neysha | 2018-09-09 | 2018-09-13 |  | Completed
2 | Andre | 2018-09-03 | 2018-09-12 |  | Completed
3 | Felix | 2018-09-10 | 2018-09-12 |  | Completed
4 | Viviana | 2018-09-11 | 2018-09-14 |  | Completed
Sprint 2 |  | 2018-09-16 | TBD |  | In progress
5 | Viviana |  |  |  | in progress
6 | Neysha/Viviana |  |  |  | in progress
7 | Neysha |  |  |  | in progress
8 | Andre/Felix |  |  |  | in progress
9 | Andre/Felix |  |  |  | in progress
Sprint 3 |  | TBD | TBD |  | Not Started
Feature 10
Feature 11
Feature 12
Feature 13
Feature 14
Feature 15
Burndown Weekly Chart
Date | Remaining | Completed | Actual Hours Done per Week
2018-08-24 | 50 | 49 | 1
2018-08-31 | 49 | 47 | 2
2018-09-07 | 47 | 44 | 3
2018-09-14 | 44 | 38 | 6
2018-09-21 | 38 | 36 | 2
2018-09-28 | 36 | 34 | 2
2018-10-05 | 34 | 30 | 4
2018-10-12 | 30 | 24 | 6
2018-10-19 | 24 | 22 | 2
2018-10-26 | 22 | 19 | 3
2018-11-02 | 19 | 16 | 3
2018-11-09 | 16 | 11 | 5
2018-11-16 | 11 | 7 | 4
2018-11-23 | 7 | 1 | 6
2018-11-30 | 1 | 0 | 1
Formulas:
ID = [ID, row above]+7